## ActionItems
ACTION ITEMS
ENMT482 Assignment 2 |  | Last Updated: | 2026-09-13 |  | Next Meeting: | 2026-06-09 11:30
ACTION ITEM | Task | OWNER | DUE | DONE | STATUS | NOTES
Pick up the Rancilio tool and place it on the Mazzer Scale pan. | a | The Don | Final Demonstration |  | Not Started
Use the Mazzer tool to unlock the Mazzer Scale | b | The Don | Milestone | √ | 100%
Use the Mazzer tool to turn the Mazzer on, wait 15s, and turn the Mazzer off. | c | The Don | Milestone |  | Not Started
Use the Mazzer tool to pull the Mazzer dosing lever until the scale reports 20±0.1g of coffee grounds has been deposited in the Rancilio tool. | d | The Don | Final Demonstration |  | Not Started
Use the Mazzer tool to lock the Mazzer Scale. | e | The Don | Final Demonstration |  | Not Started
Remove the Rancilio tool from the Mazzer. | f | The Don | Final Demonstration |  | Not Started
Open the WDT fixture, and place the Rancilio tool into the WDT fixture. | g | The Don | Final Demonstration |  | Not Started
Release the Rancilio tool and close the WDT fixture. | h | Gregsta | Final Demonstration |  | Not Started
Use the Mazzer tool to turn the WDT rotor five full revolutions. | i | Gregsta | Final Demonstration |  | Not Started
Open the WDT fixture, remove the Rancilio tool and close the WDT fixture. | j | Gregsta | Final Demonstration |  | Not Started
Place the Rancilio tool into the PUQ fixture, and wait 2 seconds while the machine tamps the coffee grounds. | k | Gregsta | Final Demonstration |  | Not Started
Remove the Rancilio tool from the PUQ fixture, and insert it into the Rancilio group head. | l | Gregsta | Final Demonstration |  | Untested
Use the Mazzer tool to operate the cup dispenser. | m | Gregsta | Milestone |  | 100%
Use the cup tool to pick up the dispensed cup, and place it on the Rancilio Scale pan. | n | Gregsta | Final Demonstration |  | Not Started
Use the Mazzer tool to unlock the Rancilio Scale. | o | Milan | Final Demonstration |  | Untested
Use the Mazzer tool to operate the Rancilio hot water switch until the scale reports 32±0.1g of water has been dispensed in the cup. | p | Milan | Final Demonstration |  | Untested
Use the Mazzer tool to lock the Rancilio Scale. | q | Milan | Final Demonstration |  | Untested
Use the cup tool to carefully pick up the cup of coffee and place it in the customer zone. | r | Milan | Final Demonstration |  | Untested
Remove the Rancilio tool from the group head. | s | Milan | Final Demonstration |  | Untested
Position the Rancilio tool over the Rancilio Tool Cleaner fixture silicone brush, and actuate for 5s. | t | Milan | Final Demonstration |  | Untested
Position the Rancilio tool over the Rancilio Tool Cleaner fixture bristle brush, and actuate for 5s. | u | Milan | Final Demonstration |  | Untested
Return the Rancilio tool to the tool stand | v | Milan | Final Demonstration |  | Untested

## Sheet1
People
Milan
The Don
Gregsta